## Tracking
Category | Activity | Start Date | End Date | Depends_On | Expected Work Effort (Hrs) | Responsibility
C | Become an Approved Shopify Design Expert |  |  |  | 37.5 | Bobby
A | Enumerate Snippet Types |  |  |  | 1 | Bobby
B | Create Snippet Liquids |  |  |  | 16 | Bobby
B | Create Article Liquid |  |  |  | 4 | Bobby
B | Create Blog Liquid |  |  |  | 4 | Bobby
B | Create Collection Liquid |  |  |  | 4 | Bobby
B | Create Featured Collection Liquid |  |  |  | 4 | Bobby
B | Create Footer Liquid |  |  |  | 4 | Bobby
B | Create Header Liquid |  |  |  | 4 | Bobby
B | Create Image Slider Liquid |  |  |  | 4 | Bobby
B | Create Logo Liquid |  |  |  | 4 | Bobby
B | Create Navigation Liquid |  |  |  | 4 | Bobby
B | Create Newsletter Liquid |  |  |  | 4 | Bobby
B | Create Product Detail Liquid |  |  |  | 4 | Bobby
B | Create Rich Text Liquid |  |  |  | 4 | Bobby
B | Create Template Liquid |  |  |  | 4 | Bobby
B | Create Testimonial Liquid |  |  |  | 4 | Bobby
B | Create Theme Product Brief |  |  |  | 4 | Bobby
A | Create UX Flowchart |  |  |  | 8 | Bobby
B | Implement Context Switching |  |  |  | 8 | Bobby
A | MockUp Desktop Wireframes |  |  |  | 16 | Bobby
A | MockUp Mobile Wireframes |  |  |  | 16 | Bobby
A | MockUp UX Wireframes |  |  |  | 16 | Bobby
A | Research How to Context Switching |  |  |  | 4 | Bobby
C | Sell Shopify Store to Cannabis Retailers |  |  |  | 37.5 | Bobby
A | Research Testing Framework |  |  |  | 4 | Bobby
B | Implement Testing Framework |  |  |  | 16 | Bobby